## Introduction
Information
Date |  | 2023-08-23
Summary
Description | Total
Test Cases | 34
BUG | 34
Suggestions | 2
Risks | 4
Automated Scenarios | 6
Manual Scenarios | 28
Technical Debt | 5

## Test Cases
Create a user.
ID | Description | Steps | Data | Prerequisite | Expected result | Result shown | Priority | Automated
CP 001 | create a user by submitting all the correct data | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/user | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | YES
CP 002 | create a user without the id field |  | 1. Servicio tipo POST. 2. { "id": , "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 003 | create a user without the username field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 004 | create a user without the firstname field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 005 | create a user without the lastname field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 006 | create a user without the email field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 007 | create a user password field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 008 | create a user without the phone field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 009 | create a user without the userStatus field |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": } |  | Status code 400 | Status code 200 | high | NO
CP 010 | create a user with an existing email address |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismieles@gmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
CP 011 | When creating a user with an incorrect email address |  | 1. Servicio tipo POST. 2. { "id": 0, "username": "elvis_m", "firstName": "Mieles", "lastName": "Guarin", "email": "elvismielesgmail.com", "password": "mieles123", "phone": "3045410190", "userStatus": 0 } |  | Status code 400 | Status code 200 | high | NO
Login
CP 012 | Logging into the system correctly | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/user/login | 1. Servicio tipo GET. 2. "username": "elvis_m" "password": "mieles123", | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | YES
CP 013 | Log in without the username field |  | 1. Servicio tipo GET. 2. "username": "" "password": "mieles123", | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
CP 014 | Log in without the password field |  | 1. Servicio tipo GET. 2. "username": "elvis_m" "password": "", | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
CP 015 | Login with incorrect username field |  | 1. Servicio tipo GET. 2. "username": "elvis_1" "password": "mieles123", | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
CP 016 | Login with incorrect password field |  | 1. Servicio tipo GET. 2. "username": "elvis_m" "password": "mieles124", | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
pet/findByStatus
CP 017 | Search for available pet status | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/pet/findByStatus | 1. Servicio tipo GET. 2. "status": "available " | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | YES
CP 018 | Search for pending pet status |  | 1. Servicio tipo GET. 2. "status": "pending " | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | NO
CP 019 | Search for pet status found sold |  | 1. Servicio tipo GET. 2. "status": "sold " | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | NO
CP 020 | Find status does not exist |  | 1. Servicio tipo GET. 2. "status": "xxxx " | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
CP 021 | Search empty status |  | 1. Servicio tipo GET. 2. "status": "" | API must be developed and in QA environment. | Status code 400 | Status code 200 | high | NO
pet
CP 022 | Search pet by id correctly | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/pet | 1. Servicio tipo GET. 2. "petId": "122333" | API must be developed and in QA environment. | Status code 200 | Status code 405 | high | YES
CP 023 | Search pet by id empty |  | 1. Servicio tipo GET. 2. "petId": "" | API must be developed and in QA environment. | Status code 200 | Status code 405 | high | NO
CP 024 | Search pet by wrong id |  | 1. Servicio tipo GET. 2. "petId": "8888888" | API must be developed and in QA environment. | Status code 200 | Status code 405 | high | NO
/store/order
CP 025 | Create a purchase order correctly | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/store/order | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity": 232432, "shipDate": "2023-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | YES
CP 026 | Create a purchase order without the id field |  | 1. Servicio tipo post. 2. { "id":, "petId": 13353434345, "quantity": 232432, "shipDate": "2023-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 027 | Create a purchase order without the field petid |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId":, "quantity": 232432, "shipDate": "2023-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 028 | Create a purchase order without the quantity field |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity":, "shipDate": "2023-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 029 | Create a purchase order without the shipDate field |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity": 232432, "shipDate": "", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 030 | Create a purchase order without the status field |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity": 232432, "shipDate": "2023-08-22T23:09:23.794Z", "status": "", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 031 | Create a purchase order without the complete field |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity": 232432, "shipDate": "2023-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
CP 032 | Create a purchase order with the previous year's shipDate field |  | 1. Servicio tipo post. 2. { "id": 121324243, "petId": 13353434345, "quantity": 232432, "shipDate": "2022-08-22T23:09:23.794Z", "status": "placed", "complete": true } | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO
Logout
CP 033 | Perform Logout correctly | 1. Open Postman. 2. Make the request by postman to the endpoint https://petstore.swagger.io/v2/user/logout | 1. Servicio tipo get. | API must be developed and in QA environment. | Status code 200 | Status code 200 | high | YES
CP 034 | Logout without logging in |  | 1. Servicio tipo get. | API must be developed and in QA environment. | Status code 200 | Status code 400 | high | NO

## Bug
Information of the request
Date of creation |  |  | 2023-08-23
Document change log
Version |  |  | Motive |  | Made |  | Date of creation
V 1.0 |  |  | Creation |  | Elvis Miguel Mieles Guarin |  | 2023-08-23
BUG
ID | Functionality | Description |  | Priority |  | State |  | Date reported
BUG 001 | Create a user. | Allows me to create without the id field |  | high |  | open |  | 2023-08-23
BUG 002 | Create a user. | Allows me to create without the username field |  | high |  | open |  | 2023-08-23
BUG 003 | Create a user. | Allows me to create without the firstName field |  | high |  | open |  | 2023-08-23
BUG 004 | Create a user. | Allows me to create without the lastName field |  | high |  | open |  | 2023-08-23
BUG 005 | Create a user. | Allows me to create without the email field |  | high |  | open |  | 2023-08-23
BUG 006 | Create a user. | Allows me to create without the password field |  | high |  | open |  | 2023-08-23
BUG 007 | Create a user. | Allows me to create without the phone field |  | high |  | open |  | 2023-08-23
BUG 008 | Create a user. | Allows me to create without with existing email field |  | high |  | open |  | 2023-08-23
BUG 009 | Create a user. | Allow me to create without with wrong email field |  | high |  | open |  | 2023-08-23
BUG 010 | Create a user. | When incomplete data is sent, the ai should display a message indicating which data is missing. |  | high |  | open |  | 2023-08-23
BUG 011 | Login | Displays a status Code 200 when sending an incorrect username |  | high |  | open |  | 2023-08-23
BUG 012 | Login | Displays a status Code 200 when sending an empty username |  | high |  | open |  | 2023-08-23
BUG 013 | Login | Displays a status Code 200 when an incorrect password is sent. |  | high |  | open |  | 2023-08-23
BUG 014 | Login | Displays a status Code 200 when sending an empty password |  | high |  | open |  | 2023-08-23
BUG 015 | Login | Displays the message logged in user session, when incorrect data is sent. |  | high |  | open |  | 2023-08-23
BUG 016 | Status | when searching for an incorrect status shows the response empty and with a status 400 |  | high |  | open |  | 2023-08-23
BUG 017 | Status | when searching for an empty status shows the response empty and with a status of 400 |  | high |  | open |  | 2023-08-23
BUG 018 | Buscar ascota | API is not responding |  | high |  | open |  | 2023-08-23
BUG 019 | Create Orden | It is allowing me to create orders with the same order ID. |  | high |  | open |  | 2023-08-23
BUG 020 | Create Orden | It is allowing me to create order without the id field |  | high |  | open |  | 2023-08-23
BUG 021 | Create Orden | It is allowing me to create order without petId field |  | high |  | open |  | 2023-08-23
BUG 022 | Create Orden | It is allowing me to create order without the quantity field |  | high |  | open |  | 2023-08-23
BUG 023 | Create Orden | It is allowing me to create order without shipDate field |  | high |  | open |  | 2023-08-23
BUG 024 | Create Orden | It is allowing me to create order without the status field |  | high |  | open |  | 2023-08-23
BUG 025 | Create Orden | It is allowing me to create order without the complete field |  | high |  | open |  | 2023-08-23
BUG 026 | Create Orden | The API is not displaying a message when it is missing some information. |  | high |  | open |  | 2023-08-23
BUG 027 | Logout | The API is not containing a token |  | high |  | open |  | 2023-08-23
BUG 028 | Logout | The API is not displaying a correct message |  | high |  | open |  | 2023-08-23

## Suggestions
Document change log
Version |  | Motive | Made | Date of creation
V 1.0 |  | Creation | Elvis Miguel Mieles Guarin | 2023-08-23
Suggestions
ID | Description |  |  | Date reported
SUG 001 | The API must contain more complete response messages |  |  | 2023-08-23
SUG 002 | In the swagger you should have more information on the possible scenarios (informative responses, successful responses, redirection messages, client error responses, server error responses). |  |  | 2023-08-23

## Risks
Document change log
Version |  | Motive |  | Made |  | Date of creation
V 1.0 |  | Creation |  | Elvis Miguel Mieles Guarin |  | 2023-08-23
Risks
ID | Description |  | Impact |  | Probability |  | Date reported | Transfer
Risks 001 | It is evident that the API's do not generate any type of TOKEN, this generates that the users can enter the system without data validation. |  | Incorrect customer information and an unsound database |  | HIGH |  | 2023-08-23 | TEAM
Risks 002 | It is likely to generate inconsistencies in the information extracted from the database due to the validations of the forms. |  | Generate errors in the visualization of the information to be consulted. |  | MEDIUM |  | 2023-08-23 | TEAM
Risks 003 | It is evident that the generator orders can always be used because it keeps available, this can generate a negative impact financially. |  | Decrease the company's profits. |  | HIGH |  | 2023-08-23 | TEAM
Risks 004 | Loss of order information is identified at the time of logout, which could lead to customer dissatisfaction. |  | Decrease sales |  | HIGH |  | 2023-08-23 | TEAM

## Technical Debt
Registro de cambios de documentos
Versiòn |  | Motivo |  | Realizado |  | Fecha de realizaciòn
V 1.0 |  | Creaciòn |  | Elvis Miguel Mieles Guarin |  | 2023-08-23
Technical Debt
ID | Description |  | Impact |  | Probability |  | Date reported | Transfer | Affected Area
Technical Debt 001 | Validate/verify API response when you have Informative Responses |  | Production release may be delayed (depending on when the development area delivers it). |  | HIGH |  | 2023-08-23 | TEAM | TEAM
Technical Debt 002 | Validate/verify API response when you have successful Responses |  |  |  | HIGH |  | 2023-08-23 | TEAM | TEAM
Technical Debt 003 | Validate/verify API response when you have Redirection Messages |  |  |  | HIGH |  | 2023-08-23 | TEAM | TEAM
Technical Debt 004 | Validate/verify API response when you have Client Error Responses |  |  |  | HIGH |  | 2023-08-23 | TEAM | TEAM
Technical Debt 005 | Validate/verify API response when you have Server Error Responses |  |  |  | HIGH |  | 2023-08-23 | TEAM | TEAM